## Sheet1
Application / Component | Migration Strategy | Target Technology | Complexity | Development (PD) | Unit Testing (PD) | Code Review (PD) | Total (PD) | Remarks
APT to PDF | Rearchitect | .NET 9 Azure Function | Medium | 8 | 2 | 1 | 11 | Replace Windows application with Azure Function
Spectra to PDF | Rearchitect | .NET 9 Azure Function | Medium | 8 | 2 | 1 | 11 | PDF generation and storage
EBR Process | Rearchitect | .NET 9 Azure Function | High | 12 | 3 | 1 | 16 | Trigger file processing and scheduling
ProcessEBRSchedule | Replatform | .NET 9 Worker Service / VM | Medium | 6 | 2 | 1 | 9 | Existing logic migrated with minimal changes
ProcessAdvices | Rearchitect | .NET 9 Azure Function | Medium | 8 | 2 | 1 | 11 | Scheduled advice generation
StatementComplianceReport | Retire | ADF Pipeline / SQL Job | Low | 3 | 1 | 0.5 | 4.5 | Replace application with SQL/ADF process
TABLOAD (sp_wtc_tabload) | Rearchitect | .NET 9 Azure Function | High | 15 | 3 | 2 | 20 | File ingestion and SQL loading
TABDUMP (sp_wtc_tabdump) | Rearchitect | .NET 9 Azure Function | High | 15 | 3 | 2 | 20 | Data extraction and file generation
File Share Service | New Development | Azure Files SDK | Medium | 5 | 1 | 0.5 | 6.5 | Upload/download services
Blob Storage Integration | New Development | Azure Blob Storage | Medium | 4 | 1 | 0.5 | 5.5 | Archive and staging storage
SQL Repository Layer | Replatform | EF Core / Dapper | Medium | 6 | 2 | 1 | 9 | Repository implementation
Logging & Monitoring | New Development | Application Insights | Low | 3 | 1 | 0.5 | 4.5 | Logging, telemetry, alerts
Authentication | Replatform | Managed Identity | Low | 2 | 1 | 0.5 | 3.5 | Azure authentication
Azure Function Project Setup | New Development | .NET 9 | Low | 2 | 0.5 | 0.5 | 3 | Common project structure
CI/CD Pipeline | New Development | Azure DevOps | Medium | 5 | 1 | 1 | 7 | Build and deployment pipeline
Configuration & Key Vault | New Development | Azure Key Vault | Low | 3 | 1 | 0.5 | 4.5 | Secrets and configuration

## Sheet2
Email Ref | Email Content | M&T Sharded Document | Queries
3.1 | Migrate to Azure the .NET utilities that process the statement types listed below 1) Accounting Statements |  | The first statement type, 'Account Statement', has already been developed using Angular for the frontend and .NET Core(9.0) APIs for the backend. The expectation is to deploy this application to Azure as-is, and no further development is required from our end for this component. Please provide the code base for the both projects .
3.2 | 2) APT & SPECTR | The SAD specifies that this functionality should be developed using .NET. | 1) "I understand that the input file should be stored in Azure File Share." 2) "Please provide a valid input file for processing, along with the expected two output PDF file types including logo image" 3) "Kindly confirm in which database the MTB_APT and MTB_SPECTR metadata schemas should be stored, considering OLS archive retirement (TBD)." 4) "Please confirm the target location for saving files—whether it should be Azure Blob Storage or Azure File Share."
3.3 | 3) EBR | SAD mentioed Employee benefit report | 1) "As per the IFR current state diagram, the scheduler runs from Tuesday to Saturday starting at 7:00 AM. Accordingly, the input file should be picked from Azure File Share, processed into PDFs, and stored in Blob Storage as outlined above. Kindly confirm." 2)"Please provide valid sample input and expected output file formats." 3)"Since this requirement involves a scheduled/timer trigger, we plan to implement it using an Azure Function." 4)"Please confirm whether metadata schemas (as discussed earlier) are not required for this functionality. If they are required, kindly confirm which database should be used, as the overview diagram suggests referring to IFD_Conv."
1.2 | Matrix below "Assumptions" |  | EBR Process (Rearchitect) and ProcessEBRSchedule (Replatform) are mentioned as two separate processes. I’m unclear why they are treated as different items, as it appears that the above scenario already covers this functionality. Kindly clarify.
3.4 | 4) SRDE | As per the SAD, this process involves stored procedures and jobs, with no implementation using .NET. | As per the SAD, this process involves stored procedures and jobs, with no implementation using .NET. However, there appears to be a discrepancy, as the diagram indicates an SEI API call. Kindly confirm the correct approach.
3.5 | 5) Advices |  | As per the SAD, this process does not involve .NET. Kindly confirm.
3.6 | 6) Compliance |  | As mentioned in the email and diagram, this process has been retired and should not be implemented in either ADF or .NET. Kindly confirm.